## Sheet1
Issue | Issue Details | Service/Port/FW | RootCause | Fix
Eureka and oauth | Eureka and oauth services are not initializing | Port Issue | The port has no access | Added the port numbers in web server security group and written background service file for both eureka and oauth
Micro services conncectivity | unable to creation connection from application web server |  |  | Created the a slave node and configure the app server in the slave node in jenkins
Start port | port number already in use | Port Issue | port number Assigned to another service | Installed the firewalld service into the web server and given port number access
eureka server | request from microservices to eureka server is not established | IP Address | Given localhost in app.properties | encountered and changed the localhost to private Ip address of app server in web server
Manual process | No Automation in application |  | No jenkins Tool | Created the jenkins and configured the applications for automation build and deployment
applications | unable to run services in the application server | Port Issue | Port number is not enabled | Given the 8080 port access into the application server and reboot the server.
website | Unable to access the website |  | nginx issue | Reinstalled the nginx server in the web server and reconfigured it.
Latest build | Unable to get latest build in tomcat |  | no script | Created the new Jenkins job and written script to automatic the latest build in to the tomcat
SSL | SSL is not working |  | Automatic updation of nginx server | included the default .config in nginx.config file and added all the content in default.config
swaggers | swaggers not working |  | application issue | removed the war files in prod and added from dev to prod and rebuilded them
Data Base connectivity issue
DMS